## Sheet1
1. Testing of new components and components with the priority of 5
Smoke test
Component | Total TestCases | % TestCases Executed | % TestCases failed
Regression test
Component | Total TestCases | % TestCases Executed | % TestCases failed
2. Testing of old components
Smoke test
Component | Total TestCases | % TestCases Executed | % TestCases failed
Notes:
1. Если нет тесткейсов - ставится цифра на глаз 2. % TestCases Executed может не быть 100% если есть баги которые закрывают какую-нибудь функциональность
3. Overall detailed statistics
New bugs
Component | Priority | Jira Link
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2579
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2580
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2582
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2583
Insert | Major | http://jira.jboss.com/jira/browse/RF-2601
List Shuttle | Critical | http://jira.jboss.com/jira/browse/RF-2613
List Shuttle | Critical | http://jira.jboss.com/jira/browse/RF-2615
Reopened bugs
Component | Priority | Jira Link
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2447
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2097
Ordering List | Minor | http://jira.jboss.com/jira/browse/RF-2090
Ordering List | Major | http://jira.jboss.com/jira/browse/RF-2238
Closed bugs
Component | Priority | Jira Link
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-1812
ListShuttle | Major | http://jira.jboss.com/jira/browse/RF-2189
ListShuttle | Major | http://jira.jboss.com/jira/browse/RF-2338
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2513
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-1808
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2239
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-1607
Ordering List | Major | http://jira.jboss.com/jira/browse/RF-2500
Ordering List | Major | http://jira.jboss.com/jira/browse/RF-1660
a4j:Status | Critical | http://jira.jboss.com/jira/browse/RF-2234
Ordering List | Major | http://jira.jboss.com/jira/browse/RF-2350
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-2350
Ordering List | Major | http://jira.jboss.com/jira/browse/RF-1659
List Shuttle | Major | http://jira.jboss.com/jira/browse/RF-1659