## Sheet1
1. Testing of new components and components with the priority of 5
Smoke test
Component | Total TestCases | % TestCases Executed | % TestCases failed
Calendar | 14 | 95 | 3
Regression test
Component | Total TestCases | % TestCases Executed | % TestCases failed
Calendar | 54 | 90 | 8
2. Testing of old components
Smoke test
Component | Total TestCases | % TestCases Executed | % TestCases failed
List Shuttle | 17 | 100 | 2
Notes:
1. Если нет тесткейсов - ставится цифра на глаз 2. % TestCases Executed может не быть 100% если есть баги которые закрывают какую-нибудь функциональность
3. Overall detailed statistics
New bugs
Component | Priority | Jira Link
List Shuttle | Critical | http://jira.jboss.com/jira/browse/RF-2422
InplaceSelect | Major | http://jira.jboss.com/jira/browse/RF-3412
InplaceSelect | Major | http://jira.jboss.com/jira/browse/RF-3398
Reopened bugs
Component | Priority | Jira Link
List Shuttle | Critical | http://jira.jboss.com/jira/browse/RF-2422
Closed bugs
Component | Priority | Jira Link
List Shuttle | Critical | http://jira.jboss.com/jira/browse/RF-2422
ComboBox | Minor | http://jira.jboss.com/jira/browse/RF-3160
ComboBox | Minor | http://jira.jboss.com/jira/browse/RF-3179
InplaceSelect | Major | http://jira.jboss.com/jira/browse/RF-3276
ComboBox | Major | http://jira.jboss.com/jira/browse/RF-3285
InplaceSelect | Major | http://jira.jboss.com/jira/browse/RF-3310
InplaceSelect | Major | http://jira.jboss.com/jira/browse/RF-3323