## Test run A
Build: | Build RF3.1.0 RC5 | Legend: | Showstopper | http://jira.jboss.com/jira/browse/RF-248
Test Started: | 2007-09-06 11:00 |  | Critical | http://jira.jboss.com/jira/browse/RF-248
Test Finshed: | 2007-09-07 16:30 |  | Major | http://jira.jboss.com/jira/browse/RF-248
Prepared By: | Alexey Morlender |  | Minor | http://jira.jboss.com/jira/browse/RF-248
Total Cases: | 26 |  | Trivial | http://jira.jboss.com/jira/browse/RF-248
Total Conf: | 4
Conclusion:
|  | Full | Full | Full | Full
|  | Pass | Pass | Pass | Pass
Configuration: | JDK 1.5 Tomcat 5.5 JSF 1.1F | IE | Firefox | Opera | Safari |  |  | Issues
Test Case: | DataFilterSlider |  |  |  |  | Pass | Full
| Data Table Scroller | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | Fail | Full | http://jira.jboss.com/jira/browse/RF-892 http://jira.jboss.com/jira/browse/RF-871 http://jira.jboss.com/jira/browse/RF-840 http://jira.jboss.com/jira/browse/RF-814 http://jira.jboss.com/jira/browse/RF-726
| Drag and Drop |  |  |  |  | Pass | Full
| DropDownMenu |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-611
| Gmap |  |  |  |  | Pass | Full
| inputNumberSlider |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-895
| inputNumberSpinner |  |  |  |  | Pass | Full
| modalPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-835
| Paint2D |  |  |  |  | Pass | Full
| Panel |  |  |  |  | Pass | Full
| PanelBar |  |  |  |  | Pass | Full
| Separator |  |  |  |  | Pass | Full
| SimpleTogglePanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-96
| Spacer |  |  |  |  | Pass | Full
| SuggestionBox |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-833 http://jira.jboss.com/jira/browse/RF-56
| TabPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-843 http://jira.jboss.com/jira/browse/RF-403 http://jira.jboss.com/jira/browse/RF-191
| TogglePanel |  |  |  |  | Pass | Full
| ToolBar |  |  |  |  | Pass | Full
| Tree |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-881 http://jira.jboss.com/jira/browse/RF-795 http://jira.jboss.com/jira/browse/RF-765 http://jira.jboss.com/jira/browse/RF-416http://jira.jboss.com/jira/browse/RF-168 http://jira.jboss.com/jira/browse/RF-88
| PanelMenu |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-885
| Calendar |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-896
| Tooltip |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-890
| Message |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-764
| Scrollable Grid |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-599
| Effect |  |  |  |  | Pass | Full
| Insert |  |  |  |  | Pass | Full
|  | Full | Full | Full | Full
|  | Pass | Pass | Pass | Pass
Configuration: | JDK 1.5 Tomcat 5.5 JSF 1.2F | IE | Firefox | Opera | Safari |  |  | Issues
Test Case: | DataFilterSlider |  |  |  |  | Pass | Full
| Data Table Scroller | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | Fail | Full | http://jira.jboss.com/jira/browse/RF-892 http://jira.jboss.com/jira/browse/RF-871 http://jira.jboss.com/jira/browse/RF-840 http://jira.jboss.com/jira/browse/RF-814 http://jira.jboss.com/jira/browse/RF-726
| Drag and Drop |  |  |  |  | Pass | Full
| DropDownMenu |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-611
| Gmap |  |  |  |  | Pass | Full
| inputNumberSlider |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-895
| inputNumberSpinner |  |  |  |  | Pass | Full
| modalPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-835
| Paint2D |  |  |  |  | Pass | Full
| Panel |  |  |  |  | Pass | Full
| PanelBar |  |  |  |  | Pass | Full
| Separator |  |  |  |  | Pass | Full
| SimpleTogglePanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-96
| Spacer |  |  |  |  | Pass | Full
| SuggestionBox |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-833 http://jira.jboss.com/jira/browse/RF-56
| TabPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-843 http://jira.jboss.com/jira/browse/RF-403 http://jira.jboss.com/jira/browse/RF-191
| TogglePanel |  |  |  |  | Pass | Full
| ToolBar |  |  |  |  | Pass | Full
| Tree |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-881 http://jira.jboss.com/jira/browse/RF-795 http://jira.jboss.com/jira/browse/RF-765 http://jira.jboss.com/jira/browse/RF-416http://jira.jboss.com/jira/browse/RF-168 http://jira.jboss.com/jira/browse/RF-88
| PanelMenu |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-885
| Calendar |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-896
| Tooltip |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-890
| Message |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-764
| Scrollable Grid |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-599
| Effect |  |  |  |  | Pass | Full
| Insert |  |  |  |  | Pass | Full
|  | Full | Full | Full | Full
|  | Pass | Pass | Pass | Pass
Configuration: | JDK 1.5 Tomcat 5.5 JSF 1.1RI | IE | Firefox | Opera | Safari |  |  | Issues
Test Case: | DataFilterSlider |  |  |  |  | Pass | Full
| Data Table Scroller | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | Fail | Full | http://jira.jboss.com/jira/browse/RF-892 http://jira.jboss.com/jira/browse/RF-871 http://jira.jboss.com/jira/browse/RF-840 http://jira.jboss.com/jira/browse/RF-814 http://jira.jboss.com/jira/browse/RF-726
| Drag and Drop |  |  |  |  | Pass | Full
| DropDownMenu | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-611
| Gmap |  |  |  |  | Pass | Full
| inputNumberSlider |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-895
| inputNumberSpinner |  |  |  |  | Pass | Full
| modalPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-835
| Paint2D |  |  |  |  | Pass | Full
| Panel |  |  |  |  | Pass | Full
| PanelBar |  |  |  |  | Pass | Full
| Separator |  |  |  |  | Pass | Full
| SimpleTogglePanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-96
| Spacer |  |  |  |  | Pass | Full
| SuggestionBox | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-833 http://jira.jboss.com/jira/browse/RF-56
| TabPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-843 http://jira.jboss.com/jira/browse/RF-403 http://jira.jboss.com/jira/browse/RF-191
| TogglePanel |  |  |  |  | Pass | Full
| ToolBar |  |  |  |  | Pass | Full
| Tree |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-881 http://jira.jboss.com/jira/browse/RF-795 http://jira.jboss.com/jira/browse/RF-765 http://jira.jboss.com/jira/browse/RF-416http://jira.jboss.com/jira/browse/RF-168 http://jira.jboss.com/jira/browse/RF-88
| PanelMenu |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-885
| Calendar | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-896
| Tooltip | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-890
| Message |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-764
| Scrollable Grid |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-599
| Effect |  |  |  |  | Pass | Full
| Insert |  |  |  |  | Pass | Full
|  | Full | Full | Full | Full
|  | Pass | Pass | Pass | Pass
Configuration: | JDK 1.5 Tomcat 5.5 JSF 1.2RI | IE | Firefox | Opera | Safari |  |  | Issues
Test Case: | DataFilterSlider |  |  |  |  | Pass | Full
| Data Table Scroller | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | http://jira.jboss.com/jira/browse/RF-871 | Fail | Full | http://jira.jboss.com/jira/browse/RF-892 http://jira.jboss.com/jira/browse/RF-871 http://jira.jboss.com/jira/browse/RF-840 http://jira.jboss.com/jira/browse/RF-814 http://jira.jboss.com/jira/browse/RF-726
| Drag and Drop |  |  |  |  | Pass | Full
| DropDownMenu | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-611
| Gmap |  |  |  |  | Pass | Full
| inputNumberSlider |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-895
| inputNumberSpinner |  |  |  |  | Pass | Full
| modalPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-835
| Paint2D |  |  |  |  | Pass | Full
| Panel |  |  |  |  | Pass | Full
| PanelBar |  |  |  |  | Pass | Full
| Separator |  |  |  |  | Pass | Full
| SimpleTogglePanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-96
| Spacer |  |  |  |  | Pass | Full
| SuggestionBox | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-833 http://jira.jboss.com/jira/browse/RF-56
| TabPanel |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-843 http://jira.jboss.com/jira/browse/RF-403 http://jira.jboss.com/jira/browse/RF-191
| TogglePanel |  |  |  |  | Pass | Full
| ToolBar |  |  |  |  | Pass | Full
| Tree |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-881 http://jira.jboss.com/jira/browse/RF-795 http://jira.jboss.com/jira/browse/RF-765 http://jira.jboss.com/jira/browse/RF-416http://jira.jboss.com/jira/browse/RF-168 http://jira.jboss.com/jira/browse/RF-88
| PanelMenu |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-885
| Calendar | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-896
| Tooltip | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | http://jira.jboss.com/jira/browse/RF-861 | Fail | Full | http://jira.jboss.com/jira/browse/RF-890
| Message |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-764
| Scrollable Grid |  |  |  |  | Pass | Full | http://jira.jboss.com/jira/browse/RF-599
| Effect |  |  |  |  | Pass | Full
| Insert |  |  |  |  | Pass | Full
Note on D13: Alexey Morlender: IE browser family
Note on D43: Alexey Morlender: IE browser family
Note on D74: Alexey Morlender: IE browser family
Note on D104: Alexey Morlender: IE browser family
Note on E13: Alexey Morlender: Manual Test ReachFaces 3.0 Build 76 JSF1.2 With Facelets Tomcat 5.5 JDK 1.5
Note on E43: Alexey Morlender: Manual Test ReachFaces 3.0 Build 76 JSF1.2 With Facelets Tomcat 5.5 JDK 1.5
Note on E74: Alexey Morlender: Manual Test ReachFaces 3.0 Build 76 JSF1.2 With Facelets Tomcat 5.5 JDK 1.5
Note on E104: Alexey Morlender: Manual Test ReachFaces 3.0 Build 76 JSF1.2 With Facelets Tomcat 5.5 JDK 1.5
Note on F13: Alexey Morlender Opera browser family
Note on F43: Alexey Morlender Opera browser family
Note on F74: Alexey Morlender Opera browser family
Note on F104: Alexey Morlender Opera browser family
Note on G13: Alexey Morlender: Safari browser family
Note on G43: Alexey Morlender: Safari browser family
Note on G74: Alexey Morlender: Safari browser family
Note on G104: Alexey Morlender: Safari browser family
Note on J13: Old still open issues
Note on J14: Old still open issues
Note on J43: Old still open issues
Note on J44: Old still open issues
Note on J74: Old still open issues
Note on J75: Old still open issues
Note on J104: Old still open issues
Note on J105: Old still open issues